## TEST PLAN
TEST PLAN
PROJECT NAME | Android app for information sharing and engagement with the audience of Cloud Counselage Pvt.Ltd.
PROJECT ID
INTERN NAME | Chayandev Bera
PROJECT MANAGER | Harshada Topale
INTRODUCTION
(Brief introduction of the test strategies, process, workflow and methodologies used for the project)
This document outlines the testing strategies, processes, workflows, and methodologies employed for the Cloud Counselage Compass app. The testing phase is a critical component of ensuring the reliability, performance, and functionality of the application.
SCOPE
IN SCOPE (Defines the features, functional or non-functional requirements of the software that will be tested)
Functional Testing: Verification of all specified functional requirements, including user registration, authentication, chatbot interactions, and profile management. Non-Functional Testing: Evaluation of performance, security, usability, and scalability aspects of the application. Compatibility Testing: Ensuring compatibility with different Android OS versions. Integration Testing: Validation of interactions between app components and external services (e.g., Firebase, Dialog Flow). User Acceptance Testing (UAT): Involving end-users to evaluate the app's usability and overall satisfaction.
OUT SCOPE (Defines the features, functional or non-functional requirements of the software that will NOT be tested)
Testing of features not explicitly mentioned in the Software Requirement Specification (SRS). Compatibility testing with non-Android platforms. Hardware-specific testing beyond the minimum requirements.
QUALITY OBJECTIVE
(Mention the overall objective that you plan to achieve without your testing)
The overall objective of our testing is to: Ensure the Cloud Counselage Compass app conforms to both functional and non-functional requirements. Guarantee that the app meets the quality specifications defined by the client. Identify and rectify any bugs or issues before the app's official launch.
ROLES AND RESPONSIBILITIES
(Detail description of the Roles and responsibilities of different team members)
QA Analyst: Responsible for test planning, test case creation, and execution. Test Manager: Oversees the testing process, resource allocation, and progress monitoring. Configuration Manager: Manages version control and configurations. Developers: Collaborate with testers to address and validate bug fixes. Installation Team: Ensures smooth installation and user onboarding. Amongst others based on project needs.
TEST METHODOLOGY
OVERVIEW (Mention the reason of adopting a particular test methodology for the project)
The Agile test methodology has been selected for the Cloud Counselage Compass app project. Agile allows for iterative testing and frequent collaboration between development and testing teams. This methodology aligns with the app's dynamic development and quick adaptation to changing requirements.
TEST LEVELS (Define the Types of Testing to be executed on the Application Under Test (AUT))
iven the project's scope and timelines, we recommend the following test levels: System Testing: Comprehensive testing to ensure the entire app functions cohesively and meets requirements.
BUG TRIAGE (Define resolution of each bug, prioritize bugs and determine a schedule for all “To Be Fixed Bugs’)
Bug triage will involve: Resolution of each bug based on priority. Prioritization of bugs for fixes. Determination of a schedule for resolving "To Be Fixed Bugs."
TEST DELIVERABLES
(Mention all the Test Artifacts that will be delivered during different phases of the testing lifecycle)
Test Plan Test Cases Requirement Traceability Matrix Bug Reports Test Strategy Test Metrics Customer Sign Off
RESOURCE AND ENVIRONMENT NEEDS
TESTING TOOLS
The following tools will be utilized: Requirements Tracking Tool Bug Tracking Tool Automation Tools (if applicable)
TEST ENVIRONMENT (Minimum hardware requirements that will be used to test the Application)
Minimum Andoid version 8 (phone testing)
ADDITIONAL COMMENTS
NA
TEST PLAN
ITEMS TO TEST | TEST DESCRIPTION | TEST START DATE | TEST END DATE | RESPONSIBLE PERSON | STATUS | COMMENTS
Functional testing | All the features of Splash screen animation,sign up,log in, | 2023-09-20 | 2023-09-28 | Project | PASSED | NA
| authenication,chat bot working, firebase data storage. |  |  | Developer
Non Functional Testing | Performance , and resposiveness of the ui | 2023-09-20 | 2809-2023 | Project | PASSED | NA
Developer
Note on C17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To determine scope, you must – > Precise customer requirement > Project Budget > Product Specification > Skills & talent of your test team
Note on C24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The objective of the testing is finding as many software defects as possible; ensure that the software under test is bug free before release. To define the test objectives, you should do 2 following steps: > List all the software features (functionality, performance, GUI…) which may need to test. > Define the target or the goal of the test based on above features
Note on C40: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: A Testing Type is a standard test procedure that gives an expected test outcome. all Testing Types are aimed at achieving one common goal “Early detection of all the defects before releasing the product to the customer. There are tons of Testing Types for testing software product. Your team cannot have enough efforts to handle all kind of testing. As Test Manager, you must set priority of the Testing Types > Which Testing Types should be focused for web application testing? > Which Testing Types should be ignored for saving cost? The commonly used testing types are: 1. Unit Testing 2. API Testing 3. Integration Testing 4. System Testing 5. Install/Uninstall Testing 6. Agile Testing You need to decide based on your project scope, time and cost the testing type(s) required for your project