## Sheet1
PROJECT CHARTER
GENERAL PROJECT INFORMATION
Project Name | Cloud Councelage Compass (Android app for information sharing and engagement with the audience of Cloud Counselage Pvt.Ltd.)
Project Sponsor | Tushar Topale
Project Manager | Harshada Topale
Expected Start Date | 2023-08-01
Expected Completion Date | 2023-09-30
Estimated Cost | NA
GOALS, OBJECTIVES, DELIVERABLES
Project Objective | Design and Develop one Android app with splash screen ,login and sign-up page and one chatbot in the home page.
Business Case | Taking fowrawd the engament to the Compnay
Goals/Metrics | Develop the android app for information sharing and engagement with the audience of Cloud Counselage Pvt.Ltd to improve user engagement and efficient access of company information.
Expected Deliverables | One fully tested app with the features of login-sign up and chat bot .
PROJECT SCOPE & SCHEDULE
Within Scope | Design different screens of the app , then start coding for the logic implementation.
Outside of Scope | Hybridization the app for multi platform
PROJECT RESOURCES & COSTS
Project Team | Chayandev Bera
Support Resources | All the FAQS From IAC website , Firebase Authentication and Firebase realtime Database.
Cost Allocation | 0
PROJECT STAKEHOLDERS & CUSTOMERS
Process Owner | Harshada Topale
Key Stakeholders | Harshada Topale
End Customers | Cloud Counselage Pvt. Ltd.
PROJECT RISKS, CONSTRAINTS & ASSUMPTIONS
Risks | Data security and privacy corners regarding user information stored in firebase.
Assumptions | One Assumption is that when user will use thai app then internet access should be accepted ot internet connection should be present to successfully get the authentication of the account and also can communicate with chat bot , because chatbot is created using Dialog flow so , when ever user will give one question input the respected reply will be fetched from the API , for that internet is important.
Constraints | AI-ML technology to implement Chat-bot
MILESTONES
Milestone 1-Requirement Gathering | 2023-08-15
Milestone 2-Planning | 2023-08-17
Milestone 3-Design | 2023-08-20
Milestone 4-Development | 2023-09-15
Milestone 5-Testing | 2023-09-25
Milestone 6-Deployment | 2023-09-28
Milestone 7-Closure | 2023-09-30