## Project Schedule
IAC Internship Progra 2023 - <Android Development> Project Schedule
|  | PROJECT START DATE | 2023-07-31
|  | Display Week Sr No | 1 | [10 empty] | 2023-07-31 | [6 empty] | 2023-08-07 | [6 empty] | 2023-08-14 | [6 empty] | 2023-08-21 | [6 empty] | 2023-08-28 | [6 empty] | 2023-09-04 | [6 empty] | 2023-09-11 | [6 empty] | 2023-09-18 | [6 empty] | 2023-09-25
|  | Document Title : | PROJECT SCHEDULE
|  | Document Created By : | Chayandev Bera
|  | Documnet Created On : | 2023-08-20
Version : 3.0
Should you face any difficulty in completing the 'Project Schedule', please refer to 'Project Planning' Workshop, https://cloudcounselage.graphy.com/sessions/Project-Planning-64af88dcb308530823e2c19f | time axis 2023-07-31 to 2023-10-01
Sr No | Week/ Duration/ Sprint/ Phase | Activities | Task | Sub Task | Dependencies | Assigned to | Start Date | End Date | Actual End Date | Hours required | Status | Progress | Comments | time axis 2023-07-31 to 2023-10-01
1 | Project Initiation week
1.1 |  | Initiation |  |  |  |  | 2023-08-05 | 2023-08-15 | 2023-08-15 |  | Completed | Done
1.1.1 |  | Initiation 1.1 | Create Project Charter |  |  |  | 2023-08-05 | 2023-08-06 | 2023-08-06 | 4 | Completed | Done
1.1.2 |  | Initiation 1.2 | Requirement Election Questionnaries |  |  |  | 2023-08-08 | 2023-08-10 | 2023-08-10 | 4 | Completed | Done
1.1.3 |  |  | Create SRS |  |  |  | 2023-08-13 | 2023-08-15 | 2023-08-15 | 4 | Completed | Done
2 | Project Planning Week
2.1 |  | Planning | [8 empty] | Completed
2.1.1 |  |  | Work Breakdown Structure |  |  |  | 16-08-20232 | 2023-08-16 | 2023-08-16 | 3 | Completed | done
2.1.2 |  |  | Raid Log |  |  |  | 2023-08-17 | 2023-08-17 | 2023-08-17 | 3 | Completed | done
2.1.3 |  |  | Baseline Project plan |  |  |  | 2023-08-18 | 2023-08-20 | 2023-08-20 | 5 | Completed | done
3 | Project Execution week
3.1 |  | Execution |  |  |  |  | 2023-08-20 | 2023-09-25 | 2023-09-25
3.1.1 |  | Design | Finalize Design | UI for each Screen |  |  | 2023-08-20 | 2023-08-25 | 2023-08-25 | 18 | Completed | Done
3.2 |  | Build | Developing all the features |  |  |  | 2023-08-26 | 2023-09-15 | 2023-09-15 | 72 | Completed | done
3.2.1 |  | Splash screen | Creating splash screen with naimation |  |  |  | 2023-08-28 | 2023-08-28 | 2023-08-28 | 1 | Completed | done
3.2.2 |  | Sign up screen | Creating Sing Up feature with error handeling | Sign up With user Input Email,username,password | Firebase authentication and realtime storage |  | 2023-08-29 | 2023-08-30 | 2023-08-30 | 4 | Completed | done
|  |  |  | Sign Up using social Google |  |  | 2023-09-01 | 2023-09-01 | 2023-09-01 | 3 | Completed | done
|  |  |  | Sign up using social Facebook | [6 empty] | On Hold
3.2.3 |  | Sign In Screen | Create Sign in Feature with error handeling | Sign in using Email and password | Firebase authentication and realtime storage |  | 2023-09-02 | 2023-09-02 | 2023-09-02 | 2 | Completed | done
|  |  |  | Implementing Forget Password and reset it |  |  | 2023-09-04 | 2023-09-04 | 2023-09-04 | 1 | Completed | done
|  |  |  | Social (google) sing in |  |  | 2023-09-04 | 2023-09-04 | 2023-09-04 | 1 | Completed
3.2.4 |  | Home Screen | Creating Home Screen with general information |  |  |  | 2023-09-06 | 2023-09-06 | 2023-09-06 | 3 | Completed
3.2.5 |  | Profile Screen | Show Profile Details | Only user name and Email | Firebase realtime Database |  | 2023-09-08 | 2023-09-08 | 2023-09-08 | 2 | Completed
|  |  |  | Adding option to update Profile Picture |  |  | 2023-09-10 | 2023-09-10 | 2023-09-10 | 4 | Completed
3.2.6 |  | Chat Bot | Interactive Chat bot implementation | Gather All FAQ from IAC |  |  | 2023-09-11 | 2023-09-12 | 2023-09-12 | 5 | Completed
|  |  |  | Add all possible Questions with possible answers to Dialog Flow Intents | Dialog Flow |  | 2023-09-12 | 2023-09-13 | 2023-09-13 | 6 | Completed
|  |  |  | Add Dependecies of Dialog flow |  |  | 2023-09-14 | 2023-09-14 | 2023-09-14 | 2 | Completed
|  |  |  | fetch replies on the basis of the user's question and show |  |  | 2023-09-15 | 2023-09-15 | 2023-09-15 | 4 | Completed
3.3 |  | Testing | Manual testing |  |  |  | 2023-09-16 | 2023-09-25 | 2023-09-25 |  | Completed
4 Closure
4.1 | Closure | [5 empty] | 2023-09-30 | 2023-09-30 | 2023-09-30 |  | In Progress
Note on H12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Nirbhey Singh Pahwa - I was thinking if we should add an actual start date column as well? Reply: Or, let's call this one as planned start date and the next one as start date. The same can be done for End date. Because, writing 'actual' feels as if we've missed some deadline of some sorts so can be avoided. You can have this in the DM Goals template for now, let me add this to the next version of this template, i.e., Goals [Template v0.5] Thank you